## ProjectSchedule
AI-Enabled Smart Library Management System
Aradhya Goyal - 1024160135 |  | Project Start: | 2026-07-29
Amanjot Kaur Sidhu - 1024160025 |  | Today: | 2026-09-09
Arnav Agarwal - 1024160010 |  | Display Week: | 1 |  |  | 2026-07-27 | [6 empty] | 2026-08-03 | [6 empty] | 2026-08-10 | [6 empty] | 2026-08-17 | [6 empty] | 2026-08-24 | [6 empty] | 2026-08-31 | [6 empty] | 2026-09-07 | [6 empty] | 2026-09-14
 | time axis 2026-07-27 to 2026-09-20
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2026-07-27 to 2026-09-20
Phase 1 - Inception, Ideation & Proposal Setup
Problem Identification & Conventional CRUD Limitations Research |  | 100% | 2026-03-08 | 2026-06-08
Multi-Agent Architectural Concept & Scope Definition |  | 100% | 2026-08-05 | 2026-08-09
Project Pitch Slide Deck Design & Proposal Presentation |  | 100% | 2026-08-10 | 2026-08-14
Formal LaTeX Project Proposal & TikZ Architecture Modeling |  | 100% | 2026-08-17 | 2026-08-23
Scope Refinement & Pivot to Smart Library System |  | 100% | 2026-08-24 | 2026-08-28
Phase 2: System Modeling & Architectural Design
Multi-Agent Roles & Task Boundaries Specification |  | 100% | 2026-08-10 | 2026-08-16
UML Use Case Diagram Engineering & Dependency Mapping |  | 100% | 2026-08-19 | 2026-08-21
3-Level Data Flow Diagrams (DFD Level 0, 1, 2) Design |  | 100% | 2026-08-24 | 2026-08-25
Database Entity & Data Store Identification (MySQL/Stores D1–D3) |  | 100% | 2026-08-26 | 2026-08-27
Operational Constraints & Measurable Evaluation Criteria Definition |  | 100% | 2026-08-27 | 2026-08-30
Phase 3: Repository Setup & Documentation Infrastructure
GitHub Repository Structure Customization & Cleanup |  | 100% | 2026-08-24 | 2026-08-26
MkDocs Material Theme, Navigation & Styling Configuration |  | 80% | 2026-08-31 | 2026-09-02
CI/CD Automation via GitHub Actions for Documentation |  | 100% | 2026-09-02 | 2026-09-04
GitHub Pages Deployment (gh-pages Branch Configuration) |  | 100% | 2026-09-04 | 2026-09-05
Master Schedule & Gantt Tracking Setup |  | 80% | 2026-09-05 | 2026-09-06
Phase 4 Title
Task 1 |  |  | 2019-01-29 | 2019-02-03
Task 2 |  |  | 2019-01-29 | 2019-02-02
Task 3 |  |  | 2019-02-03 | 2019-02-06
Task 4 |  |  | 2019-02-03 | 2019-02-06
Task 5 |  |  | 2019-02-07 | 2019-02-11
Phase 5 Title
Task 1 |  |  | 2019-02-05 | 2019-02-10
Task 2 |  |  | 2019-02-05 | 2019-02-07
Task 3 |  |  | 2019-02-08 | 2019-02-13
Task 4 |  |  | 2019-02-08 | 2019-02-13
Task 5 |  |  | 2019-02-08 | 2019-02-12
Insert new rows ABOVE this one
SIMPLE GANTT CHART by Vertex42.com |  |  |  | 2018-01-13
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2018-2019 Vertex42 LLC

## About
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2018-2019 Vertex42 LLC
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
► Watch How This Gantt Chart Was Created
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.